WORK PLAN

Work Plan for development of CMIS

| S.No. | Event | Expected date |
| --- | --- | --- |
| 1. | Draft Framework for Designing CMIS | March 01 |
| 2. | System Requirement Study (SRS) for finalizing various options (hardware, software and connectivity both at Center and States) for designing CMIS software | April 01 |
| 3. | Draft Indicators and Input Formats for CMIS on the following aspect of the programme: - Blood Safety - Targeted Interventions - STD Management - Voluntary Counselling and Testing - NGO (C&S) - Information, Education and Communication - SACS/MACS - Programme Management | May 01 |
| 4. | Development of CMIS- CMIS software designed based on completed SRS and data flow channel | June 01 |
| 5. | Workshop with SACS/MACS for finalizing indicators and input formats at Bangalore; A brief demo of the emerging CMIS software was also presented to SACS/MACS | June 01 |
| 6. | Draft output Formats for CMIS on the following aspect of the programme: 1 Blood Safety 2. Targeted Interventions - STD Management - Voluntary Counseling and Testing - NGO (C&S) - Information, Education and Communication - SACS/MACS - Programme Management | July 01 |
| 7. | Placement of Information Co-ordinators at all the SACS/MACS except J & K and the new SACS | Aug-Sep. 01 |
| 8. | Installation of CMIS software with all standard features at SACS/MACS | Nov. 01 |
| 9. | The training Manual for usages of CMIS | Dec. 01 |
| 10. | Comprehensive 3 days Hands on Training of SACS functionaries in four locations | Dec. 01 |
| 11. | Launch and operationalisation of NACO Website with the software update provision on the website itself | Jan. 02 |

Work Plan for the General Population Survey

| Sl. No. | Detailed Activities | Deadline |
| --- | --- | --- |
| 1 | Development of sampling information format | Feb 1-7 |
| 2 | Finalisation of sampling information format | Feb 8-10 |
| 3 | Development of Questionnaire | Feb 11-15 |
| 4 | Translation and back translation of questionnaire | Feb 16-23 |
| 5 | Rapid qualitative research | Feb 19- 24 |
| 6 | Project orientation workshop | Feb 26-28 |
| 7 | Pre-testing exercise in four States, Uttar Pradesh, Maharashtra, West Bengal and Tamil Nadu | 3 March -8 March |
| 8 | Finalisation of Questionnaire based on findings of pre-testing exercise | 10- 14 March |
| 9 | Four zonal training workshops in Delhi, Bhopal, Kolkata and Chennai. | 15 March – 6 April |
| 10 | The state – level training workshops for field investigators and supervisors will be organised in each State or State Group. (5days). | April 9-13 |
| 11 | Initiation of field works April –May ( Delhi, Rajasthan, UP, Bihar, Orissa, WB, Goa, Gujarat, Maharshtra, Kerala, Tamil Nadu) May-June ( Haryana, HP, Punjab, Assam, Manipur, MP) June- July ( J & K, Other NE states) July –Aug ( Karnataka) August- Sept ( AP) | 15 April ( Phase-1: 11 states) Phase –II (16June: 11 states) |
| 12 | Finalisation of DE program | 15/5/01 |
| 13 | Preparation of Tabulation Plan | 30/5/01 |
| 14 | Finalisation of DE program | 15/6/01 |
| 15 | Preparation of Tabulation Plan | 30/6/01 |
| 16 | Preparation of report | 1- 15 October |

| S. No. | State | No. of Districts |
| --- | --- | --- |
| 1 | Andhra Pradesh | 4 |
| 2 | Arunchal Pradesh | 2 |
| 3 | Assam | 4 |
| 4 | Bihar | 6 |
| 5 | Chandigarh | 1 |
| 6 | Delhi | 1 |
| 7 | Goa | 2 |
| 8 | Daman | 1 |
| 9 | Gujarat | 4 |
| 10 | Haryana | 3 |
| 11 | Himachal Pradesh | 3 |
| 12 | Jammu & Kashmir | 2 |
| 13 | Karnataka | 4 |
| 14 | Lakshadeep | 1 |
| 15 | Maharashtra | 5 |
| 16 | Manipur | 2 |
| 17 | Meghalaya | 2 |
| 18 | Mizoram | 2 |
| 19 | Madhya Pradesh | 6 |
| 20 | Nagaland | 2 |
| 21 | Orissa | 3 |
| 22 | Punjab | 3 |
| 23 | Rajasthan | 4 |
| 24 | Sikkim | 2 |
| 25 | Tamil Nadu | 5 |
| 26 | Tripura | 1 |
| 27 | Uttar pradesh | 6 |
| 28 | West Bengal | 4 |

Number of districts selected by States for the General Population Survey

Work Plan for the High Risk and Bridge Population Survey

| Sl. No. | Detailed Activities | Deadline |
| --- | --- | --- |
| 1 | Development of sampling information format (FSW and Client) | 6/7/01 |
| 2 | Questionnaires- 2nd draft | 13/7/01 |
| 3 | Finalisation of sampling information format (FSW and Client) | 13/7/01 |
| 4 | Collection of sampling info in 12 States (FSW and Client) | 17/7/01 – 31/7/01 |
| 5 | Questionnaires- 3rd draft (pilot) | 7/8/01 |
| 6 | Instruction Manual- first draft (FSW and Client) | 15/8/01 |
| 7 | Meeting of ORG-CSR’s HRG Core Team | 16/8/01 – 18/8/01 |
| 8 | PILOT Survey (FSW and Client) at four locations | 21/8/01- 31/8/01 |
| 9 | Scrutiny, Coding and Analysis of Pilot data | 1/9/01- 15/9/01 |
| 10 | Sampling for first five states (FSW and Client) | 13/9/01 |
| 11 | NGO/Community Networking in first five states (FSW and Client) | 13/9/01 onwards |
| 12 | TOT in Delhi | 20/9/01- 22/9/01 |
| 13 | Questionnaires- final draft (FSW and Client) | 24/9/01 |
| 14 | Translated version of the questionnaires for FSW and Clients – final draft (first five states) | 25/9/01 |
| 15 | Questionnaires – final (FSW and Client) | 31/9/01 |
| 16 | Instruction Manual- final (FSW and Client) | 31/9/01 |
| 17 | Note on Sampling-first five states (FSW and Client) | 31/9/01 |
| 18 | Cluster Information Sheets (FSW and Client) | 31/9/01 |
| 19 | Training Workshop for FSW and Clients of FSW (Five States to be covered in Phase I) | 1/10/01- 7/10/01 |
| 20 | Fieldwork for FSW and Clients (Five States to be covered in Phase I) | 10/10/01- 31/10/01 |
| 21 | Collection of sampling info in the remaining states (FSW and Client) | 15/10/01- 21/10/01 |
| 22 | Sampling for FSW and Client- Phase II | 22/10/01 |
| 23 | NGO/Community Networking for FSW and Client- Phase II | 23/10/01 onwards |
| 24 | Translated version of the questionnaires for IDU and MSM (first two locations) | 13/10/01 |
| 25 | Translated version of the questionnaires for FSW and Clients – final draft (Phase II) | 15/10/01 |
| 26 | Collection of sampling info for IDU and MSM | 15/10/01- 31/10/01 |
| 27 | PILOT Survey (IDU and MSM) | 15/10/01- 21/10/01 |
| 28 | Training workshop for FSW and Clients (Five States to be covered in Phase II) | 22/10/01- 27/10/01 |
| 29 | Scrutiny, Coding and Analysis of Pilot data (IDU and MSM) | 22/10/01- 31/10/01 |
| 30 | Note on Sampling for FSW and Client- Phase II | 31/10/01 |
| 31 | Translated version of the questionnaires for FSW and Clients – final draft (Phase III) | 31/10/01 |
| 32 | Fieldwork for FSW and Clients (Five States to be covered in Phase II) | 2/11/01- 17/11/01 |
| 33 | Sampling for first two states (IDU and MSM) | 4/11/01 |
| 34 | Sampling for FSW and Client- Phase III | 4/11/01 |
| 35 | NGO/Community Networking for IDU and MSM- Phase I | 5/11/01 onwards |
| 36 | NGO/Community Networking for FSW and Client- Phase III | 5/11/01 onwards |
| 37 | Questionnaires – final draft (IDU and MSM) | 6/11/01 |
| 38 | Instruction Manual- final draft (IDU and MSM) | 7/11/01 |
| 39 | Note on Sampling for IDU and MSM- Phase I | 9/11/01 |
| 40 | Cluster Information Sheets (IDU and MSM) | 9/11/01 |
| 41 | Note on Sampling for FSW and Client- Phase III | 10/11/01 |
| 42 | Training Workshop for IDU (Phase I – 2 locations) | 12/11/01- 16/11/01 |
| 43 | Training workshop for FSW and Clients (Six States to be covered in Phase III) | 12/11/01- 17/11/01 |
| 44 | Fieldwork for IDU (Phase I – 2 locations) | 19/11/01- 7/12/01 |
| 45 | Fieldwork for FSW and Clients (Six States to be covered in Phase III) | 19/11/01- 10/12/01 |
| 46 | Training Workshop for MSM (Phase I – 2 locations) | 19/11/01- 23/11/01 |
| 47 | Sampling for IDU and MSM- Phase II | 20/11/01 |
| 48 | NGO/Community Networking for IDU and MSM- Phase II | 21/11/01 onwards |
| 49 | Sampling for FSW and Client- Phase IV | 24/11/01 |
| 50 | NGO/Community Networking for FSW and Client- Phase IV | 25/11/01 onwards |
| 51 | Fieldwork for MSM (Phase I – 2 locations) | 26/11/01- 15/12/01 |
| 52 | Translated version of the questionnaires for IDU and MSM – final draft (Phase II) |  |
| 53 | Note on Sampling for IDU and MSM- Phase II | 26/11/01 |
| 54 | Translated version of the questionnaires for FSW and Clients – final draft (Phase IV) | 30/11/01 |
| 55 | Training Workshop for IDU (Phase II – 3 locations) | 27/11/01- 1/12/01 |
| 56 | Fieldwork for IDU (Phase II – 3 locations) | 4/12/01- 21/12/01 |
| 57 | Training Workshop for MSM (Phase II–3 locations) | 3/12/01- 8/12/01 |
| 58 | Fieldwork for MSM (Phase II – 3 locations) | 11/12/01- 31/12/01 |
| 59 | Note on Sampling for FSW and Client- Phase IV | 2/12/01 |
| 60 | Training workshop for FSW and Clients (Six States to be covered in Phase IV) | 3/12/01- 8/12/01 |
| 61 | Fieldwork for FSW and Clients (Six States to be covered in Phase IV) | 11/12/01- 31/12/01 |
| 62 | Finalisation of DE program – FSW and Client | 15/10/01 |
| 63 | Preparation of Tabulation Plan- FSW and Client | 31/10/01 |
| 64 | Finalisation of DE program – IDU and MSM | 15/11/01 |
| 65 | Preparation of Tabulation Plan- IDU and MSM | 30/11/01 |
| 66 | Completion of entire fieldwork (all states and categories) | 31/12/01 |
| 67 | All India Top-line Presentation | 15/1/02 |